## Gantt Chart
Advanced Portable Text Search
PROJECT TITLE |  | CEN 4090L Group Project | [9 empty] | COMPANY NAME | [6 empty] | Gitgud
TEAM MEMBERS | [11 empty] | DATE | [6 empty] | 2022-09-16
Sara Hertz, Malachi McInvale, Matthew Scragg, Zayn Severance, Nicholas Weisson
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [19 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 0 (SEPT) |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 (OCT) |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 (NOV) |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 (DEC)
[7 empty] | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 1 | 2
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
| Project start |  | 2022-09-05 |  |  | 0% | bar: WEEK 0 (SEPT) 5 M; WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 11 23 W
| Group Meetings |  | 2022-09-05 | 2022-12-02 | 87 | 0% | bar: WEEK 0 (SEPT) 8 R; WEEK 1 13 T to WEEK 1 14 W; WEEK 2 19 M to WEEK 2 23 F; WEEK 3 28 W; WEEK 4 (OCT) 5 W; WEEK 5 10 M to WEEK 5 14 F; WEEK 6 19 W; WEEK 7 26 W; WEEK 9 9 W; WEEK 10 16 W; WEEK 11 23 W; WEEK 12 (DEC) 30 W
2 | Requirements Research
| Language Selection |  | 2022-09-12 | 2022-09-30 | 18 | 0% | bar: WEEK 1 12 M to WEEK 3 30 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 11 23 W
| Grammar Parsing |  | 2022-09-12 | 2022-09-30 | 18 | 0% | bar: WEEK 1 12 M to WEEK 3 30 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 11 23 W
| Runtime Optimization |  | 2022-09-12 | 2022-09-30 | 18 | 0% | bar: WEEK 1 12 M to WEEK 3 30 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 11 23 W
| Front-End UI Development |  | 2022-09-12 | 2022-09-30 | 18 | 0% | bar: WEEK 1 12 M to WEEK 3 30 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 11 23 W
3 | Preliminary Design
| Basic Search Function (Tier 0) |  | 2022-09-12 | 2022-10-07 | 25 | 0% | bar: WEEK 1 12 M to WEEK 5 14 F; WEEK 11 23 W
| Acrobat-like Search Function (Tier 1) |  | 2022-09-26 | 2022-10-14 | 18 | 0% | bar: WEEK 2 19 M to WEEK 5 14 F; WEEK 11 23 W
| Enhanced Function (Tier 2) |  | 2022-10-10 | 2022-10-28 | 18 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 8 (NOV) 4 F; WEEK 11 23 W
4 | Back-End Development
| File Input and Parsing |  | 2022-09-12 | 2022-10-07 | 25 | 0% | bar: WEEK 1 12 M to WEEK 5 14 F; WEEK 11 23 W
| User Input: Keyword and Context Integration |  | 2022-09-19 | 2022-10-07 | 18 | 0% | bar: WEEK 2 19 M to WEEK 5 14 F; WEEK 11 23 W
| Search Algorithms |  | 2022-09-19 | 2022-10-14 | 25 | 0% | bar: WEEK 2 19 M to WEEK 5 14 F; WEEK 11 23 W
| Indexing Algorithms |  | 2022-10-10 | 2022-10-28 | 18 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 8 (NOV) 4 F; WEEK 11 23 W
| Statistical Analysis |  | 2022-09-26 | 2022-10-07 | 11 | 0% | bar: WEEK 2 19 M to WEEK 5 14 F; WEEK 11 23 W
5 | Front-End UI Development
| Display basic search results w/ Context scores |  | 2022-09-19 | 2022-10-07 | 18 | 0% | bar: WEEK 2 19 M to WEEK 5 14 F; WEEK 11 23 W
| Menu |  | 2022-09-12 | 2022-10-07 | 25 | 0% | bar: WEEK 1 12 M to WEEK 5 14 F; WEEK 11 23 W
| Interactive Views |  | 2022-10-10 | 2022-10-28 | 18 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 8 (NOV) 4 F; WEEK 11 23 W
| Rolling Results |  | 2022-10-10 | 2022-10-28 | 18 | 0% | bar: WEEK 2 19 M to WEEK 5 14 F; WEEK 11 23 W
| Statistical Result View |  | 2022-10-10 | 2022-10-28 | 18 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 8 (NOV) 4 F; WEEK 11 23 W
6 | Testing
| Unit testing |  | 2022-10-03 | 2022-10-21 | 18 | 0% | bar: WEEK 1 12 M to WEEK 6 21 F; WEEK 11 23 W
| Integration testing |  | 2022-10-24 | 2022-11-11 | 17 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 9 11 F; WEEK 11 23 W
| Product testing |  | 2022-11-14 | 2022-11-30 | 16 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 8 (NOV) 31 M to WEEK 12 (DEC) 30 W
7 | Integration
| Back-End Results Input to Front-End UI |  | 2022-10-03 | 2022-10-21 | 18 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 4 (OCT) 3 M to WEEK 6 21 F; WEEK 11 23 W
| Front-End UI Input to Back-End |  | 2022-09-19 | 2022-11-11 | 52 | 0% | bar: WEEK 2 19 M to WEEK 3 30 F; WEEK 5 10 M to WEEK 6 21 F; WEEK 8 (NOV) 31 M to WEEK 9 11 F; WEEK 11 23 W
8 | Final Delivery
| Delivery |  | 2022-11-30 | 2022-12-02 | 2 | 0% | bar: WEEK 2 19 M to WEEK 2 23 F; WEEK 5 10 M to WEEK 5 14 F; WEEK 11 23 W; WEEK 12 (DEC) 30 W to WEEK 12 (DEC) 2 F

## Form Responses 1
Timestamp | Untitled Question